## List
PMP TEMPLATES
STT | Name | Name | link
1.1 | Project Charter | 1.1 Điều lệ dự án | #'1.1 Project Charter'!Print_Area
1.2 | Assumption Log | 1.2 Nhật kí giả định | #'1.2 Assumption Log'!Print_Area
1.3 | Stakeholder Register | 1.3 Các bên liên quan ký | #'1.3 Stakeholder Register'!Print_Area
1,4 | Stakeholder Analysis | 1,4 Phân tích bên liên quan | #'1.4 Stakeholder Analysis'!Print_Area
2.1 | Project Management plan | 2.1 Quản lý kế hoạch dự án | #'2.1 Project Management Plan'!Print_Area
2.2 | Change management plan | 2.2 Quản lý thay đổi | #'2.2 CHANGE MANAGEMENT PLAN'!Print_Area
2.4 | Scope management plan | 2.4 Phạm vi kế hoạch quản lý | #'2.24 Quality'!Print_Area
2.5 | Requirement management plan | 2.5 Yêu cầu quản lý kế hoạch | #'2.5 Requirements Management Pla'!Print_Area
2,6 | Requirement document | 2,6 Yêu cầu Tài liệu | #'2.6 Requirements Documentation'!Print_Area
2.7 | Requirement Traceability | 2.7 Yêu cầu truy xuất nguồn gốc | #'2.7 Requirements Traceability'!Print_Area
2.8 | Project scope Statement | 2.8 Tuyên bố phạm vi dự án | #'2.8 Project Scope Statement'!Print_Area
2.10 | WBS Dictionary | 2.10 WBS điển | #'2.10 WBS Dictionary'!Print_Area
2.11 | Schedule Management Plan | 2.11 Quản lý kế hoạch lịch tình | #'2.11 Schedule Management Plan'!Print_Area
2.12 | Activity list | 2.12 Hoạt động Danh sách | #'2.12 Activity List'!Print_Area
2.13 | Activity attributes | 2.13 Hoạt động Thuộc tính | #'2.13 Activity Attributes'!Print_Area
2.14 | Milestone list | 2.14 Danh sách cột mốc | #'2.14 Milestone List'!Print_Area
2.16 | Duration estimates | 2.16 Ước tính thời lượng | #'2.16 Duration Estimates'!Print_Area
2.17 | Duration estimating worksheet | 2.17 Ước tính thời lượng ... | #'2.17 Duration Estimating ...'!Print_Area
2.19 | Cost management plan | 2.19 Kế hoạch quản lý | #'2.19 Cost Management Plan'!Print_Area
2.20 | Activity cost estimates | 2.20 Dự toán chi phí | #'2.20 Cost Estimates'!Print_Area
2.21 | Cost estimating worksheet | 2.21 Bảng tính dự toán chi phí | #'2.21 Cost Estimating Worksheet'!Print_Area
2.23 | Quality management plan | 2.23 Kế hoạch quản lý chất lượng | #'2.23 Quality Management Plan'!Print_Area
2.24 | Quality management plan | 2.24 Kế hoạch quản lý Chất lượng | #'2.24 Quality'!Print_Area
2.25 | Responsibility assignment matrix | 2.25 Ma trận phân chia trách nhiệm | #'2.25 Responsibility Assiqnment '!Print_Area
2,26 | Resource management plan | 2,26 Quản trị nguồn nhân Kế hoạch | #'2.26 Resource Management Plan'!Print_Area
2,27 | Team charer | 2,27 Đội Điều lệ | #'2.27 Team Charter'!Print_Area
2,28 | Resource requirements | 2,28 Yêu cầu nguồn lực | #'2.28 Resource Requirements'!Print_Area
2.30 | Communications management plan | 2.30 Quản lý Truyền thông | #'2.30 Communications Management'!Print_Area
2,31 | Risk management plan | 2,31 Quản lý rủi ro Kế hoạch | #'2.31 Risk Management Plan '!Print_Area
2,32 | Risk register | 2,32 Đăng kí rủi ro | #'2.32 Risk Register'!Print_Area
2.33 | Risk management plan | 2.33 Báo cáo rủi ro | #'2.33 Risk Report'!Print_Area
2,34 | Probability and impact risk rating | 2,34 Xác suất và tác động rủ ro | #'2.34 Probability and Impact '!Print_Area
2.35 | Probability and impact matrix | 2.35 Xác suất và tác động ma trận | #'2.35 Probability and Impact Ma '!Print_Area
2,36 | Risk data sheet | 2,36 Bản dữ liệu rủi ro | #'2.36 Risk Data Sheet'!Print_Area
2.37 | Procurement management plan | 2.37 Quản lý kế hoạch mua sắm | #'2.37 Procurement Management'!Print_Area
2,38 | Procurement strategy | 2,38 Chiến lược mua sắm | #'2.38 Procurement Strategy'!Print_Area
2,39 | Source selection criteria | 2,39 Nguồn tiêu chí lựa chọn | #'2.39 Source Selection Criteria'!Print_Area
2.40 | Stakeholder engagement plan | 2.40 Sự tham gia của các bên liên quan | #' 2.40 Stakeholder Engagement'!Print_Area
3.1 | Issue log | 3.1 Nhật ký phát hành | #'3.1 Issue Log'!Print_Area
3.2 | Decision log | 3.2 Nhật ký quyết định | #'3.2 Decision Log'!Print_Area
3.3 | Change request | 3.3 Yêu cầu thay đổi | #'3.3 Change Request'!Print_Area
3.4 | Change log | 3.4 Nhật ký thay đổi | #'3.4 Change Log'!Print_Area
3.5 | Lessons learned register | 3.5 Bài học đã đăng ký | #'3.5 Lessons Learned Register'!Print_Area
3.6 | Quality audit | 3.6 Kiểm toán chất lượng | #'3.6 Quality Audit'!Print_Area
3.7 | Team performance assessment | 3.7 Đánh giá hiệu suất của | #'3.7 Team Performance Assessment'!Print_Area
4.1 | Team member status report | 4.1 Báo cáo tình trạng thành viên nhóm | #'4.1 Team Member Status Report'!Print_Area
4.2 | Project status report | 4.2 Báo cáo tình trạng dự án | #'4.2 Project Status Report'!Print_Area
4.3 | Variance analysis | 4.3 Phân tích Phương | #'4.3 Variance Analysis'!Print_Area
4.4 | Earned value analysis report | 4.4 Báo cáo phân tích giá trị thu được | #'4.4 Earned Value Analysis Repor'!Print_Area
4,5 | Risk audit | 4,5 Kiểm toán rủi ro | #'4.5 Risk Audit'!Print_Area
4.6 | Contractor status report | 4.6 Báo cáo tình trạng thầu | #'4.6 Contractor Status Report'!Print_Area
4.7 | Procurement audit | 4.7 Kiểm toán quy trình | #'4.7 Procurement Audit'!Print_Area
4.8 | Contract closeout | 4.8 Đóng hợp đồng | #'4.8 Contract Closeout'!Print_Area
4.9 | Formal acceptance form | 4.9 Chính thức chấp nhận Mẫu | #'4.9 Formal Acceptance Form'!Print_Area
5.1 | Lessons learned summary | 5.1 Tóm tắt Bài học kinh nghiệm | #'5.1 Lessons Learned Summary'!Print_Area
5.2 | Project closeout | 5.2 Đóng Dự án | #'5.2 Project or Phase Closeout'!Print_Area
6.1 | Product vision | 6.1Tầm nhìn sản phẩm | #'6.1 Product Vision'!Print_Area
6.2 | Product backlog | 6.2 Sản phẩm tồn đọng | #'6.2 Product Backlog'!Print_Area
6.4 | Retrospective | 6.4 Hồi tưởng | #'6.4 Retrospective'!Print_Area

## 1.1 Project Charter
PROJECT CHARTER |  | Trở về
Project Title: _________________________________________________________________________________
Project Sponsor: ____________________________________ Date Prepared: ________________________________
Project Manager: ___________________________________ Project Customer: ________________________________
Project Purpose:
High-Level Project Description:
Project Boundaries:
Key Deliverables:
High-Level Repuirements:
Overall Project Risk:
Page 1 of 4
PROJECT CHARTER
|  |  |  | Project Objectives | Success Criteria
Scope:
Time
Cost:
Other:
|  |  |  | Summary Milestones | Due Date
Page 2 of 4
PROJECT CHARTER
Preapproved Financial Resources:
[7 empty] | Stakeholder(s) | Role
Project Exit Criteria:
Project Manager Authority Level:
Staffing Decisions:
Budget Management and Variance:
Page 3 of 4
PROJECT CHARTER
Technical Decisions:
Conflict Resolution:
Sponsor Authority:
Approvals:
[10 empty] | ______________________________________________ | ____________________________________________
[10 empty] | Project Manager Signature | Sponsor or Originator Signature
[10 empty] | __________________________________________________ | ______________________________________________
[10 empty] | Project Manager Name | Sponsor or Originator Name
[10 empty] | _______________________________________________________ | ____________________________________________________________
[10 empty] | Date | Date
Page 4 of 4

## 1.2 Assumption Log
| ASSUMPTION LOG | [7 empty] | Trở về
Project Title: ________________________________ Date Prepared: ______________________________________________________________
| ID | Category | Assumption/constraint | Responsible Party | Due Date | Actions | Status | Comments
Page 1 of 1

## 1.3 Stakeholder Register
| STAKEHOLDER REGISTER | [5 empty] | Trở về
Project Title: ________________________________ Date Prepared: ______________________________________________________________
| Name | Position/Role | Contact Information | Repuirements | Expectations | Classification
Page 1 of 1

## 1.4 Stakeholder Analysis
| STAKEHOLDER ANALYSIS |  |  |  | Trở về
Project Title: ________________________________ Date Prepared: ______________________________________________________________
| Name or Role | Interest | Influence | Attitude
Page 1 of 1

## 2.1 Project Management Plan
| PROJECT MANAGEMENT PLAN | [5 empty] | Trở về
Project Title: ________________________________ Date Prepared: ______________________________________________________________
Project Life Cycle:
| Phase |  | Key Activities |  | Key Deliverables
| Phase | Reviews |  | Entry Criteria |  | Exit Criteria
Development Approaches:
| Deliverable |  |  | Development Approach
Subsidiary Management Plana
| Name |  |  | Comment
Scope
Time
Cost
Quality
Resource
Communications
Risk
Procurement
Stakeholder
Other Plans
Page 1 of 2
PROJECT MANAGEMENT PLAN
Variance Thresholds:
| Scope Variance Threshold |  |  | Scope Baseline Management
| Schedule Variance Threshold |  |  | Schedule Baseline Management
| Cost Variance Threshold |  |  | Cost Baseline Management
Baselines:
Attach all project baselines.
Page 2 off 2

## 2.2 CHANGE MANAGEMENT PLAN
CHANGE MANAGEMENT PLAN |  |  |  |  | Trở về
Project Title: __________________________ Date Prepared: _______________________________________
Change Management Approach:
Definitions of Change:
Schedule change:
Budget change:
Scope change:
Project document change:
Change Control Board:
| Name | Role | Responsibility | Authority
Change Control Process:
Change request submittal
Change request tracking
Change request review
Change request disposition
Attach relevant forms used in the change control process.
Page 1 of 1

## 2.4 Scope Management Plan
SCOPE MANAGEMENT PLAN | Trở về
Project Title: ____________________________ Date: ______________________________________________
Work Breakdown (WBS) Structure
WBS Dictionary
Scope Baseline Maintenance
Deliverable Acceptance
Scope and Requirements Integration
Page 1 of 1

## 2.5 Requirements Management Pla
REQUIREMENTS MANAGEMENT PLAN
Project Title: ____________________________ Date: ______________________________________________
Collection:
Analysis:
Categories:
Documentation:
Prioritization:
Page 1 of 2
REQUIREMENTS MANAGEMENT PLAN | Trở về List
Metrics:
Traceability Structure:
Tracking:
Reporting:
Validation:
Configuration Management:
Page 2 of 2

## 2.6 Requirements Documentation
REQUIREMENTS DOCUMENTATION | [8 empty] | Trở về List
Project Title: __________________________________ Date Prepared: _____________________________________________________________
| ID | Requirement | Stakeholder | Category | Priority | Acceptance Criteria | Test or Verification | Phase or Release
Page 1 of 1

## 2.7 Requirements Traceability
REQUIREMENTS TRACEABILITY MATRIX | [9 empty] | Trở về List | INTER-REQUIREMENTS TRACEABILITY MATRIX
| Project Title: ____________________________________ Date Prepared: _____________________________________________________________ | [10 empty] | Project Title: _______________________________________ Date Prepared: _____________________________________________________________
| ID | Requirement | Source | Priority | Category | Business Objective | Deliverable | Verification | Validation |  |  | ID | Business Requirement | Priority | Source | ID | Technical Requirement | Priority | Source
| Page 1 of 2 | [10 empty] | Page 2 of 2

## 2.8 Project Scope Statement
PROJECT SCOPE STATEMENT |  | Trở về List
Project Title: _____________________________ Date Prepared: ______________________________________________
Project Scope Description:
Project Deliverables:
Product Acceptance Criteria:
Project Exclusions:
Page 1 of 2
PROJECT SCOPE STATEMENT
Project Constraints:
Project Assumptions:
Page 2 of 2

## 2.10 WBS Dictionary
WBS DICTIONARY | [10 empty] | Trở về List
Project Title: _________________________________ Date Prepared: _____________________________________________________________________
| Work Package Name: |  |  | Code of Accounts:
| Description of Work: |  |  | Assumptions and Constraints:
| Milestones: 1. 2 3. |  |  | Due Dates:
| ID | Activity | Resource | Labor |  |  | Material |  |  | Total Cost
|  |  |  | Hours | Rate | Total | Units | Cost | Total
Quality Requirements:
Acceptance Criteria:
Technical Information:
Agreement Information:
Page 1 of 1

## 2.11 Schedule Management Plan
SCHEDULE MANAGEMENT PLAN |  |  |  | Trở về List
Project Title: __________________________________ Date: ______________________________________________
Schedule Methodology:
Scheduling Tools:
| Level of Accuracy: | Units of Measure: | Variance Thresholds:
Schedule Reporting and Format:
Organizational Procedure Links:
Schedule Updates:
Page 1 of 1

## 2.12 Activity List
ACTIVITY LIST |  |  |  | Trở về List
Project Title: _____________________________ Date Prepared: ______________________________________________
| ID | Activity | Description of Work
Page 1 of 1

## 2.13 Activity Attributes
ACTIVITY ATTRIBUTES | [7 empty] | Trở về List
Project Title: ____________________________________ Date Prepared: ______________________________________________________________________
| ID: | Activity:
Description of Work:
| Predecessors | Relationship | Lead or Lag | Successor |  | Relationship | Lead or Lag
| Number and Type of Team Resources Required: |  | Skill Requirements: |  | Required Resources:
Type of Effort:
Location of Performance:
Imposed Dates of Other Constraints:
Assumptions:
Page 1 of 1

## 2.14 Milestone List
MILESTONE LIST |  |  |  | Trở về List
Project Title: ___________________________ Date Prepared: ____________________________________________
| Milestone | Milestone Description | Type
Page 1 of 1

## 2.16 Duration Estimates
DURATION ESTIMATES |  |  |  |  | Trở về List
Project Title: _________________________ Date Prepared: ____________________________________________
| ID | Activity Description | Effort Hours | Duration Estimate
Page 1 of 1

## 2.17 Duration Estimating ...
DURATION ESTIMATING WORKSHEET | [6 empty] | Trở về List
Project Title: __________________________ Date Prepared: ___________________________________________________
Parametric Estimates
| ID | Effort Hours | Resource Quantity | % Available | Performance Factor | Duration Estimate
Analogous Estimates
| ID | Previous Activity | Previous Duration | Current Activity | Multiplier | Duration Estimate
Three-Point Estimates
| ID | Optimistic Duration | Most Likely Duration | Pessimistic Duration | Weighting Equation | Expected Duration Estimate
Page 1 of 1

## 2.19 Cost Management Plan
COST MANAGEMENT PLAN |  |  |  | Trở về List
Project Title: __________________________ Date Prepared: _________________________________________________
| Units of Measure: | Level of Precision: | Level of Accuracy:
Organizational Procedure Links:
Control Thresholds:
Rules of Performance Measurement:
Cost Reporting and Format:
Additional Details:
Page 1 of 1

## 2.20 Cost Estimates
ACTIVITY COST ESTIMATES | [11 empty] | Trở về List
Project Title: ____________________________________________________ Date Prepared: _____________________________________________________________________________________
| WBS ID | Resource | Labor Costs | Physical Costs | Reserve | Estimate | Method | Assumptions/ Constraints | Basis of Estimates | Range | Confidence Level
Page 1 of 1

## 2.21 Cost Estimating Worksheet
COST ESTIMATING WORKSHEET
Project Title: ___________________________ Date Prepared: _______________________________________________________
Parametric Estimates
| ID | Cost variable | Cost per Unit | Number of Unit | Cost Estimate
Analogous Estimates
| ID | Previpus Activity | Previous Cost | Current Activity | Multiplier | Cost Estimate
Three-Point Estimates
| ID | Optimistic Cost | Most Likely Cost | Pessimistic Cost | Weighting Equation | Expected Cost Estimate
Page 1 of 2
[7 empty] | COST ESTIMATING WORKSHEET | [12 empty] | Trở về List
Project Title: __________________________________________ Date Prepared: ____________________________________________________________________________________________________________________________________
[8 empty] | ID | Labor Hours | Labor Rate | Total Labor | Material | Supplies | Equipment | Travel | Other Direct Costs | Indirect Costs | Reserve | Estimate
Page 2 of 2

## 2.23 Quality Management Plan
QUALITY MANAGEMENT PLAN
Project Title: ___________________________ Date Prepared: ____________________________________________________
Quality Standards
Quality Objectives
| Metric or Specification | Measure
| 1. | 1.
| 2. | 2.
| 3. | 3.
| 4. | 4.
Quality Roles and Responsibilities
| Roles | Responsibilities
| 1. | 1.
| 2. | 2.
| 3. | 3.
Page 1 of 2
QUALITY MANAGEMENT PLAN |  |  | Trở về List
Deliverables and Processes Subject to Quality Review
| Deliverables | Processes
Quality Management Approach
Quality Control Approach
Applicable Quality Procedures
Page 2 of 2

## 2.24 Quality
QUALITY MANAGEMENT PLAN |  |  |  |  | Trở về List
Project Title: ___________________________ Date Prepared: ____________________________________________________
| ID | Item | Metric | Measurement Method
Page 1 of 1

## 2.25 Responsibility Assiqnment
RESPONSIBILITY ASSIGNMENT MATRIX | [6 empty] | Trở về List
Project Title: ________________________ Date Prepared: ________________________________________
|  | Person 1 | Person 2 | Person 3 | Person 4 | Etc.
| Work package 1 | R | C | A
| Work package 2 |  | A |  | I | R
| Work package 3 |  | R | R | A
| Work package 4 | A | R | I | C
| Work package 5 | C | R | R |  | A
| Work package 6 | R |  | A | I
| Etc. | C | A |  | R | R
R = Responsible: The person performing the work.
C = Consult: The person who has information necessary to complete the work.
A = Accountable: The person who is answerable to the project manager that the work is done on time, meets requirements, and is acceptable.
I = Inform: This person should be notified when the work is complete.
Page 1 of 1

## 2.26 Resource Management Plan
RESOURCE MANAGEMENT PLAN |  |  |  |  | Trở về List
Project Title: ______________________________ Date Prepared: _______________________________________________
Team Member Identification and Estimates
| Role | Number |  | Skill Level
| 1. | 1. |  | 1.
| 2. | 2. |  | 2.
| 3. | 3. |  | 3.
| 4. | 4. |  | 4.
| 5. | 5. |  | 5.
| 6. | 6. |  | 6.
| Staff Acquisition |  | Staff Release:
Reles, Responsibilities and Authority
| Role | Responsibility |  | Authority
| 1. | 1. |  | 1.
| 2. | 2. |  | 2.
| 3. | 3. |  | 3.
| 4. | 4. |  | 4.
| 5. | 5. |  | 5.
| 6. | 6. |  | 6.
Project Organizational Structure
Page 1 of 2
RESOURCE MANAGEMENT PLAN
Training Requirements
Rewards and Recognition
Team Development
Physical Resource Identification and Estimates
[7 empty] | Resource | Amount | Grade
[7 empty] | 1. | 1. | 1.
[7 empty] | 2. | 2. | 2.
[7 empty] | 3. | 3. | 3.
[7 empty] | 4. | 4. | 4.
[7 empty] | 5. | 5. | 5.
[7 empty] | 6. | 6. | 6.
Resource Acquisition
Resource Management
Page 2 of 2

## 2.27 Team Charter
TEAM CHARER |  | Trở về List
Project Title: ______________________________ Date Prepared: _______________________________________________
Team Values and Principles:
1.
2.
3.
4.
5.
Meeting Guidelines:
1.
2.
3.
4.
5.
Communication Guidelines:
1.
2.
3.
4.
5.
Decision-Making Process:
Page 1 of 2
RESOURCE MANAGEMENT PLAN
Conflict Resolution Process:
Other Agreements:
|  |  |  | Signature: | Date:
|  |  |  | ______________________________________________________________ | _____________________________
|  |  |  | ______________________________________________________________ | _____________________________
|  |  |  | ______________________________________________________________ | _____________________________
|  |  |  | ______________________________________________________________ | _____________________________
|  |  |  | ______________________________________________________________ | _____________________________
|  |  |  | ______________________________________________________________ | _____________________________
|  |  |  | ______________________________________________________________ | _____________________________
|  |  |  | ______________________________________________________________ | _____________________________
|  |  |  | ______________________________________________________________ | _____________________________
|  |  |  | ______________________________________________________________ | _____________________________
Page 2 of 2

## 2.28 Resource Requirements
RESOURCE REQUIREMENTS | [5 empty] | Trở về List
Project Title: _____________________________________________ Date Prepared: _________________________________________________________
| ID | Resource | Quantity | Assumpitions | Comments
Page 1 of 1

## 2.30 Communications Management
COMMUNICATIONS MANAGEMENT PLAN | [5 empty] | Trở về List
Project Title: _________________________________________________ Date Prapared: _______________________________________________
| Stakeholder | Information | Method | Timing or Frequency | Sender
| Assumptions |  | Constraints
Glossary of Terms or Acronyms:
Attach relevant Communication diagrams or flowcharts.
Page 1 of 1

## 2.31 Risk Management Plan
RISK MANAGEMENT PLAN |  |  | Trở về List
Project Title: ______________________________________ Date Prepared: _______________________________________________
Strategy
Methodology
Roles and Responsibilities
| Role | Responsibility
| 1. | 1.
| 2. | 2.
| 3. | 3.
| 4. | 4.
Risk Categories
Risk Management Funding
Contingency Protocols
Page 1 of 4
RISK MANAGEMENT PLAN
Project Title: __________________________________ Date Prepared: _______________________________________________
Frequency and Timing
Stakeholder Risk Tolerances
Risk Tracking and Audit
Page 2 of 4
RISK MANAGEMENT PLAN
Definitions of Probability
Very High
High
Medium
Low
Very Low
Definitions of Impact by Objective
[8 empty] | Scope | Quality | Time | Cost
Very High
High
Medium
Low
Very Low
Page 3 of 4
RISK MANAGEMENT PLAN
Probability and Impact Matrix
Very High
High
Medium
Low
Very Low
[14 empty] | Very Low | Low | Medium | High | Very High
Page 4 of 4

## 2.32 Risk Register
RISK REGISTER | [19 empty] | Trở về List
Project Title: _________________________________________________________________ Date Prepared: ________________________________________________________________________
| ID | Risk Statement |  |  |  | Owner |  |  | Probability |  | Impact |  |  |  |  | Scope |  | Response
[11 empty] | Scope | Quanlity |  | Schedule | Cost
| Revised Probability |  | Impact |  |  |  |  | Revised Score |  | Responsible Party |  |  | Actions |  |  |  | Status |  | Comments
|  |  | Scope | Quality | Schedule |  | Cost
Page 1 of 1

## 2.33 Risk Report
RISK MANAGEMENT PLAN | [7 empty] | Trở về List
Project Title: __________________________________ Date Prepared: _______________________________________________
Executive Summary
Overall Project Risk Overall Risk Status and Trends
| Significant Drivers of Overall Risk |  |  |  | Recommended Responses
Individual Project Risks Indicate the number of individual risks in each box below
VH
H
M
L
| VL | VL | L | M |  | H | VH
Page 1 of 4
RISK MANAGEMENT PLAN
Metrics
Number of scope risk
Number of schedule risks
Number of cost risks
Number of quality risks
Number of very high probability risks
Number of high probability risks
Number of medium probability risks
Number of active risks
Newly closed risks
Critical Risks
[10 empty] | Top Risks | Responses
[10 empty] | 1. | 1.
[10 empty] | 2. | 2.
[10 empty] | 3. | 3.
[10 empty] | 4. | 4.
[10 empty] | 5. | 5.
Changes to Critical Risks
Page 2 of 4
RISK REPORT
Quantitative Analysis Summary
Probability of Meeting Objectives
[13 empty] | Scope | Schedule |  | Cost |  | Quality |  | Other
Range of Outcomes
[13 empty] | Range of Schedule Outcomes |  |  |  | Range of Cost Outcomes
[13 empty] | Key Drivers of Variances |  |  |  | Proposed Responses
Reserve Status
[13 empty] | Total Cost Reserve |  | Used to Date |  | Used This Period |  | Remaining Reserve
[13 empty] | Total Schedule Reserve |  | Used to Date |  | Used This Period |  | Remaining Reserve
Page 3 of 4
RISK REPORT
Assessment of Reserve Adequacy
Risk Audit Summary
Summary of Risk Events
Summary of Risk Management Processes
Summary of Recommendations
Page 4 of 4

## 2.34 Probability and Impact
PROBABILITY AND IMPACT RISK RATING |  | Trở về List
Project Title: __________________________________ Date Prepared: _______________________________________________
Scope Impact
Very High
High
Medium
Low
Very Low
Quality Impact
Very High
High
Medium
Low
Very Low
Schedule Impact
Very High
High
Medium
Low
Very Low
Page 1 of 2
PROBABILITY AND IMPACT RISK RATING
Cost Impact
Very High
High
Medium
Low
Very Low
Probability
Very High
High
Medium
Low
Very Low
Risk Rating
High
Medium
Low
Page 2 of 2

## 2.35 Probability and Impact Ma
PROBABILITY AND IMPACT MATRIX | [6 empty] | Trở về List
Project Title: _______________________________________________ Date Prepared: __________________________________________________
Very High
High
Medium
Low
Very Low
|  | Very Low | Low | Medium | High | Very High
Page 1 of 1

## 2.36 Risk Data Sheet
RISK DATA SHEET | [9 empty] | Trở về List
Project Title: ______________________________________________ Date Prepared: ___________________________________________________________
| Risk ID: | Risk Description:
| Status: | Risk Cause:
| Probability | Impact |  |  |  | Score |  | Responses
|  | Scope | Quality | schedule | Cost
| Revised Probability | Revised Impact |  |  |  | Revised Score |  | Responsible Party | Actions
|  | Scope | Quality | schedule | Cost
Secondary Risks:
Residual Risk:
| Contingency Risk: | [5 empty] | Contingency Funds:
Contingency Time:
Fallback Plans:
Comments:
Page 1 of 1

## 2.37 Procurement Management
PROCUREMENT MANAGEMENT PLAN
Project Title: ___________________________________________ Date: _______________________________________
Procurement Integration
| Area | Integration Approach
Scope
Schedule
Documentation
Risk
Reporting
Timing of Key Procurement Activities
| Date | Activity
Performance Metrics
| Item | Metric | Measurement Method
Page 1 of 2
|  |  |  | PROCUREMENT MANAGEMENT PLAN |  |  |  | Trở về List
Roles, Responsibility, and Authority
[5 empty] | Roles | Responsibility | Authority
Assumptions and Constraints
[5 empty] | Category | Assumptions/Constraints
Legal Jurisdiction and Currency
Independent Estimates
Risk Management
Prequalified Sellers
1.
2.
3.
4.
Page 2 of 2

## 2.38 Procurement Strategy
PROCUREMENT STRATEGY | [9 empty] | Trở về List
Project Title: _____________________________________________________ date: _________________________________________________________
Delivery Method
Contract Type
| FFP | FPIF | FP-EPA | CPFF | CPIF | CPAF | T&M |  | Other
| Incentive or Award Fee |  | Criteria
Procurement Life Cycle
| Phase | Entry Criteria | Key Deliverables or Milestones |  |  | Exit Criteria |  | Knowledge Transfer
Page 1 of 1

## 2.39 Source Selection Criteria
SOURCE SELECTION CRITERIA | [12 empty] | Trở về List
Project Title: ______________________________________________ Date Prepared: ________________________________________________
|  |  | 1 |  | 2 |  | 3 |  | 4 |  | 5
Criterion 1
Criterion 2
Criterion 3
Criterion 4
Criterion 5
|  | Weight |  | Candidate 1 Rating |  | Candidate 1 Score | Candidate 2 Rating | Candidate 2 Score |  | Candidate 3 Rating |  | Candidate 3 Score
Criterion 1
Criterion 2
Criterion 3
Criterion 4
Criterion 5
Totals
Page 1 of 1

## 2.40 Stakeholder Engagement
STAKEHOLDER ENGAGEMENT PLAN
Project Title: __________________________________________________________ Date Prepared: _______________________________________
| Stakeholder | Unaware | Resistant | Neutral | Supportive | Leading
C = Current level of engagement D = Desired level of engagement
Pending Stakeholder Changes
Stakeholder Relationchips
Page 1 of 2
[7 empty] | STAKEHOLDER ENGAGEMENT PLAN |  |  | Trở về List
Stakeholder Engagement Approach
[8 empty] | Stakeholder | Approach
Page 2 of 2

## 3.1 Issue Log
ISSUE LOG | [9 empty] | Trở về List
Project Title: ______________________________________ Date Prepared: ____________________________
| Issue ID | Type |  | Issue Description |  |  | Priority | Impact on Objectives
| Responsible Party |  | Status |  | Res, Date | Final Resolution |  |  | Comments
Page 1 of 1

## 3.2 Decision Log
DECISION LOG | [6 empty] | Trở về List
Project Title: _______________________________________ Date Prepared: ____________________________
| ID | Category | Decision | Responsible Party | Date | Comments
Page 1 of 1

## 3.3 Change Request
CHANGE REQUEST |  |  |  |  | Trở về List
Project Title: ___________________________________________ Date Prepared: _______________________
Requestor:
Category:
| Scope | Quality | Requirements
| Cost | Schedule | Documents
Detailed Description of Proposed Change
Juslification for Proposed Change
Impacts of Change
| Scope | Increase | Decrease | Modify
Description:
| Quality | Increase | Decrease | Modify
Description:
Page 1 of 3
CHANGE REQUEST
[7 empty] | Requirements | Increase | Decrease | Modify
Description:
[7 empty] | Cost | Increase | Decrease | Modify
Description:
[7 empty] | Schedule | Increase | Decrease | Modify
Description:
[7 empty] | Stakeholder Impact | High risk | Low risk | Medium risk
Description: Project Documents
Comments
Page 2 of 3
CHANGE REQUEST
[12 empty] | Requirements | Approve | Defer | Reject
Justification
Page 3 of 3

## 3.4 Change Log
CHANGE LOG | [7 empty] | Trở về List
Project Title: ________________________________________________________ Date Prepared: ______________________________________
| ID | Category | Description of Change | Requestor | Submission Date | Status | Disposition
Page 1 of 1

## 3.5 Lessons Learned Register
LESSONS LEARNED REGISTER | [6 empty] | Trở về List
Project Title: __________________________________________________________ Date Prepared: ___________________________________________
| ID | Category | Trigger | Lesson | Responsible Party | Comments
Page 1 of 1

## 3.6 Quality Audit
QUALITY AUDIT | [7 empty] | Trở về List
Project Title: _________________________________________ Date Prepared: ______________________________
Project Auditor: ______________________________________ Audit Date: __________________________________
Area Audited:
|  | Project processes |  |  | Project documents
|  | Product documents |  |  | Project documentation
|  | Quality management plan |  |  | Defect/deficiency repair
Organizational policies and procedures
Good Practices from Similar Projects:
Areas for Improvement:
Deficiencies or Defects:
| ID |  | Defect | Action |  | Responsible Party | Due Date
Comments:
Page 1 of 1

## 3.7 Team Performance Assessment
TEAM PERFORMANCE ASSESSMENT | [5 empty] | Trở về List
Project Title: _______________________________________ Date Prepared: _________________________________
Technical Performance
| Scope | Exceeds | Meets Expectations | Needs Improvement
Comments:
| Quality | Exceeds | Meets Expectations | Needs Improvement
Comments:
| Schedule | Exceeds | Meets Expectations | Needs Improvement
Comments:
| Cost | Exceeds | Meets Expectations | Needs Improvement
Comments:
Page 1 of 3
TEAM PERFORMANCE ASSESSMENT
Interpersonal Competency
[6 empty] | Communication | Exceeds Expectations | Meets Expectations | Needs Improvement
Comments:
[6 empty] | Collaboration | Exceeds Expectations | Meets Expectations | Needs Improvement
Comments:
[6 empty] | Conflict Management | Exceeds Expectations | Meets Expectations | Needs Improvement
Comments:
[6 empty] | Decision Making | Exceeds Expectations | Meets Expectations | Needs Improvement
Comments:
Page 2 of 3
TEAM PERFORMANCE ASSESSMENT
[11 empty] | Team Morale | Exceeds Expectations |  | Meets Expectations |  | Needs Improvement
Comments:
Areas for Development
[11 empty] | Area |  | Approach |  | Actions
Page 3 of 3

## 4.1 Team Member Status Report
TEAM MEMBER STATUS REPORT |  |  | Trở về List
Project Title: __________________________________ Date Prepared: __________________________________
Team Member: ________________________________ Role: __________________________________________
Activities Planned for This Reporting Period
1.
2.
3.
4.
5.
6.
Activities Accomplished This Reporting Period
1.
2.
3.
4.
5.
6.
Activities Planned but Not Accomplished This Reporting Period
1.
2.
3.
4.
Page 1 of 3
TEAM MEMBER STATUS REPORT
Root Causw of Activity Variances
Funds Spent This Reporting Period
Funds Planned to Be Spent This Reporting Period
Root Cause of Cost Variances
Quality Variances Identified This Period
Planned Corrective or Preventive Action
Page 2 of 3
TEAM MEMBER STATUS REPORT
Activities Planned for Next Reporting Period
1.
2.
3.
4.
5.
Costs Planned for Next Reporting Period
New Risks Identified
Risk
New Issues Identified
Issue
Comments
Page 3 of 3

## 4.2 Project Status Report
PROJECT STATUS REPORT |  |  | Trở về List
Project Title: ______________________________ Date Prepared: ____________________________________
Project Manager: ___________________________ Sponsor: __________________________________________
Accomplishments for This Reporting Period
1.
2.
3.
4.
5.
6.
Accomplishments Planned but Not Completed This Reporting Period
1.
2.
3.
4.
Root Cause of Variances
Page 1 of 4
PROJECT STATUS REPORT
Impact to Upcoming Milestones or Project Due Date
Planned Corrective or Preventive Action
Funds Spent This Reporting Period
Root Cause of Variances
Page 2 of 4
PROJECT STATUS REPORT
Impact to Overall Budget or Contingency Funds
Planned Corrective or Preventive Action
Accomplishments Planned for Next Reporting Period
1.
2.
3.
4.
Costs Planned for Next Reporting Period
Page 3 of 4
[6 empty] | PROJECT STATUS REPORT |  | Trở về
New Risks Identified
Risk:
Issues
Issue:
Comments
Page 4 of 4

## 4.3 Variance Analysis
VARIANCE ANALYSIS |  |  |  |  | Trở về List
Project Title: ___________________________________ Date Prepared: ________________________________---
Schedule Variance
| Planned Result | Actual Result | Variance
Root Cause
Planned Response
Cost Variance
| Planned Result | Actual Result | Variance
Page 1 of 2
VARIANCE ANALYSIS
Root Cause
Planned Response
Quality Variance
[5 empty] | Planned Result | Actual Result | Variance
Root Cause
Planned Response
Page 2 of 2

## 4.4 Earned Value Analysis Repor
EARNED VALUE ANALYSIS REPORT |  |  |  |  | Trở về List
Project Title: __________________________________________ Date Prepared: _________________________________________--
Budget at Completion (BAC): _____________________________ Overall Status: _________________________________________---
|  | Currend Reporting Period | Currend Period Cumulative | Past Period Cumulative
Planned value (PV)
Earned value (EV)
Actual cost (AC)
Schedule variance (SV)
Cost variance (CV)
Schedule performance index (SPI)
Cost performance index (CPI)
Root Cause of Schedule Variance:
Schedule Impact:
Root Cause of Cost Variance:
Budget Impact:
Percent planned
Percent earned
Percent spent
Estimates at Completion (EAC):
EAC w/CPI [BAC/CPI]
EAC w/ CPI*SPI [AC + ((BAC - EV)/ (CPI*SPI))]
Selected EAC, Justification, and Explanation
To complete performance index (TCPI)
Page 1 of 1

## 4.5 Risk Audit
RISK AUDIT | [5 empty] | Trở về List
Project Title: ___________________________________ Date Prepared: _____________________________________________---
Project Auditor: _________________________________ Audit Date: __________________________________________________--
Risk Event Audit
| Event |  | Cause | Response | Comment
Risk Response Audit
| Event |  | Response | Successful | Actions to Improve
Risk Management Process Audit
| Process | Followed |  | Tools and Techniques Used
Plan Risk Management
Identify Risks
Perform Qualitative Assessment
Perform Quantitative Assessment
Plan Risk Responses
Monitor and Control Risks
Page 1 of 2
RISK AUDIT
Description of Good Practices to Share
Description of Areas for Improvement
Page 2 of 2

## 4.6 Contractor Status Report
CONTRACTOR STATUS REPORT |  | Trở về List
Project Title: __________________________________ Date Prepared: ___________________________________-
Vendor: ______________________________________ Contract #: ______________________________________
Scope Performance This Reporting Period
Quality Performance This Reporting Period
Schedule Performance This Reporting Period
Page 1 of 3
CONTRACTOR STATUS REPORT
Cost Performance This Reporting Period
Forecast Performance for Future Reporting Periods
Clalms or Disputes
Risks
Page 2 of 3
CONTRACTOR STATUS REPORT
Planned Corrective or Preventive Action
Issues
Comments
Page 3 of 3

## 4.7 Procurement Audit
PROCUREMENT AUDIT |  |  |  | Trở về List
Project Title: ____________________________________ Date Prepared: _______________________________-
Project Auditor: __________________________________ Audit Date: _________________________________
Vendor Performance Audit
What Worked Well:
scope
Quality
Schedule
Cost
Other
What Can Be Improved:
Scope
Quality
Schedule
Cost
Other
Procurement Management Process Audit
| Process | Followed | Tools and Techniques Used
Plan Procurements
Conduct Procurements
Control Procurements
Page 1 of 2
PROCUREMENT AUDIT
Description of Good Practices to Share
Description of Areas for Improvement
Page 2 of 2

## 4.8 Contract Closeout
CONTRACT CLOSEOUT |  |  |  | Trở về List
Project Title: _________________________________ Date Prepared: _______________________________--
Project Manager: ______________________________ Contract Representative: ____________________
Vendor Performance Analysis
What Worked Well:
Scope
Quality
Schedule
Cost
Other
What Can Be Improved:
Scope
Quality
Schedule
Cost
Other
Record of Contract Changes
| Change ID | Change Description | Date Approved
Page 1 of 2
CONTRACT CLOSEOUT
Record of Contract Disputes
| Description | Resolution | Date Resolve
Date of Contract Completion _________________________________________
Signed Off by ______________________________________________________
Date of Final Payment _______________________________________________
Page 2 of 2

## 4.9 Formal Acceptance Form
FORMAL ACCEPTANCE FORM | [7 empty] | Trở về List
Project Title: ________________________________________________________ Date Prepared: ________________________________________----
| ID | Requirement | Acceptance Criteria | Validation Method | Status | Comments | Sign-off
Page 1 of 1

## 5.1 Lessons Learned Summary
LESSONS LEARNED SUMMARY
Project Title: _________________________________ Date Prepared: ________________________________________
Project Performance Analysis
|  | What Worked Well | What Can Be Improved
Requirements definition and management
Scope definition and management
Schedule development and control
Cost estimating and control
Quality planning and control
Physical resource planning and control
Team planning, development and performance
Communications management
Reporting
Risk management
Procurement planning and management
Stakeholder engagement
Process improvement information
Product-specific information
Other
Page 1 of 2
|  |  |  | LESSONS LEARNED SUMMARY | [6 empty] | Trở về List
Risks and Issuses
[5 empty] | Risk or Issue Description |  | Response |  | Comments
Quality Defects
[5 empty] | Defect Description |  | Resolution |  | Comments
Vendor Management
[5 empty] | Vendor | Issue |  | Resolution |  | Comments
Other
[5 empty] | Areas of Exceptional Performance |  |  | Areas for Improvement
Page 2 of 2

## 5.2 Project or Phase Closeout
PROJECT CLOSEOUT |  |  | Trở về List
Project Title: ______________________________________ Date Prepared: ___________________ Project Manager: ________________________________
Project Description
Page 1 of 2
PROJECT CLOSEOUT
Performance Summary
|  |  |  | Objectives |  | Completion Criteria |  | How Met
Scope
Quality
|  |  | Variances | Objectives/Final Outcome |  | Variances |  | Comments
Time
Cost
Benefits Management
Business Needs
Risks and Issues
|  |  | Risks or Issue |  | Response or Resolution |  | Comments
Page 2 of 2

## 6.1 Product Vision
PRODUCT VISION |  | Trở về List
Project Title: ______________________________________ Date Prepared: _____________________________
We are developing this product for __________________________________________________________________
To respond to the following need(s):
*
*
*
This product responds to those needs by providing the following:
*
*
*
*
Customers will buy this product because:
*
*
*
*
Page 1 of 1

## 6.2 Product Backlog
PRODUCT BACKLOG | [5 empty] | Trở về List
Project Title: ____________________________________________________________ Date Prepared: _______________________________________
| ID | Summary Description | Priority | Story | Status
Page 1 of 1

## 6.4 Retrospective
RETROSPECTIVE | [5 empty] | Trở về List
Project Title: ________________________________________________ Date Prepared: _________________________________________________
| Start | Stop | Keep | More | Less
Page 1 of 1